## Gantt Chart
Building Nawalakw Cultural Healing Centre | [11 empty] | Gantt Chart (By Weeks)
[12 empty] | Jul-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Sep-2022 | Sep-2022 | Sep-2022 | Sep-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Feb-2023 | Feb-2023 | Feb-2023 | Feb-2023 | Mar-2023 | Mar-2023 | Mar-2023 | Mar-2023 | Apr-2023 | Apr-2023 | Apr-2023 | Apr-2023 | May-2023 | May-2023 | May-2023 | May-2023 | May-2023 | Jun-2023 | Jun-2023 | Jun-2023 | Jun-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Aug-2023 | Aug-2023 | Aug-2023 | Aug-2023 | Sep-2023 | Sep-2023 | Sep-2023 | Sep-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Mar-2024 | Mar-2024 | Mar-2024 | Mar-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | May-2024 | May-2024 | May-2024 | May-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Oct-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Nov-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Dec-2024 | Jan-2025 | Jan-2025 | Jan-2025 | Jan-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | May-2025 | May-2025 | May-2025 | May-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jul-2025 | Jul-2025 | Jul-2025 | Jul-2025 | Aug-2025 | Aug-2025 | Aug-2025 | Aug-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Oct-2025 | Oct-2025 | Oct-2025 | Oct-2025 | Nov-2025 | Nov-2025 | Nov-2025 | Nov-2025 | Dec-2025 | Dec-2025 | Dec-2025 | Dec-2025 | Dec-2025 | Jan-2026 | Jan-2026 | Jan-2026 | Jan-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | May-2026 | May-2026 | May-2026 | May-2026 | Jun-2026 | Jun-2026 | Jun-2026 | Jun-2026 | Jun-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026 | Jul-2026
[12 empty] | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
Status | ID | SID | Title | [6 empty] | Duration | Description | 25: none - This month
| 2 | 0 | Building Nawalakw Cultural Healing Centre |  |  |  |  | 2022-08-01 | 30-Jun-2026 | 4 Years | Building a healing centre, rejuvenating kwak̓wala language, in three phases. |  | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26) | item #1 (01-Aug-22 - 30-Jun-26)
| 3 | 1 | Phase 1 |  |  |  |  | 01-Aug-2022 | 31-Jan-2024 | 1.5 Years | Building small connecting road, temporary barge ramps, fire pit, docks, solar panels, buildings, and camps for consultants & working professionals. | 1: item #2 (01-Aug-22 - 31-Jan-24); 8: item #2 (01-Aug-22 - 31-Jan-24); 15: item #2 (01-Aug-22 - 31-Jan-24); 22: item #2 (01-Aug-22 - 31-Jan-24); 29: item #2 (01-Aug-22 - 31-Jan-24); 5: item #2 (01-Aug-22 - 31-Jan-24); 12: item #2 (01-Aug-22 - 31-Jan-24); 19: item #2 (01-Aug-22 - 31-Jan-24); 26: item #2 (01-Aug-22 - 31-Jan-24); 3: item #2 (01-Aug-22 - 31-Jan-24); 10: item #2 (01-Aug-22 - 31-Jan-24); 17: item #2 (01-Aug-22 - 31-Jan-24); 24: item #2 (01-Aug-22 - 31-Jan-24); 31: item #2 (01-Aug-22 - 31-Jan-24); 7: item #2 (01-Aug-22 - 31-Jan-24); 14: item #2 (01-Aug-22 - 31-Jan-24); 21: item #2 (01-Aug-22 - 31-Jan-24); 28: item #2 (01-Aug-22 - 31-Jan-24); 5: item #2 (01-Aug-22 - 31-Jan-24); 12: item #2 (01-Aug-22 - 31-Jan-24); 19: item #2 (01-Aug-22 - 31-Jan-24); 26: item #2 (01-Aug-22 - 31-Jan-24); 2: item #2 (01-Aug-22 - 31-Jan-24); 9: item #2 (01-Aug-22 - 31-Jan-24); 16: item #2 (01-Aug-22 - 31-Jan-24); 23: item #2 (01-Aug-22 - 31-Jan-24); 30: item #2 (01-Aug-22 - 31-Jan-24); 6: item #2 (01-Aug-22 - 31-Jan-24); 13: item #2 (01-Aug-22 - 31-Jan-24); 20: item #2 (01-Aug-22 - 31-Jan-24); 27: item #2 (01-Aug-22 - 31-Jan-24); 6: item #2 (01-Aug-22 - 31-Jan-24); 13: item #2 (01-Aug-22 - 31-Jan-24); 20: item #2 (01-Aug-22 - 31-Jan-24); 27: item #2 (01-Aug-22 - 31-Jan-24); 3: item #2 (01-Aug-22 - 31-Jan-24); 10: item #2 (01-Aug-22 - 31-Jan-24); 17: item #2 (01-Aug-22 - 31-Jan-24); 24: item #2 (01-Aug-22 - 31-Jan-24); 1: item #2 (01-Aug-22 - 31-Jan-24); 8: item #2 (01-Aug-22 - 31-Jan-24); 15: item #2 (01-Aug-22 - 31-Jan-24); 22: item #2 (01-Aug-22 - 31-Jan-24); 29: item #2 (01-Aug-22 - 31-Jan-24); 5: item #2 (01-Aug-22 - 31-Jan-24); 12: item #2 (01-Aug-22 - 31-Jan-24); 19: item #2 (01-Aug-22 - 31-Jan-24); 26: item #2 (01-Aug-22 - 31-Jan-24); 3: item #2 (01-Aug-22 - 31-Jan-24); 10: item #2 (01-Aug-22 - 31-Jan-24); 17: item #2 (01-Aug-22 - 31-Jan-24); 24: item #2 (01-Aug-22 - 31-Jan-24); 31: item #2 (01-Aug-22 - 31-Jan-24); 7: item #2 (01-Aug-22 - 31-Jan-24); 14: item #2 (01-Aug-22 - 31-Jan-24); 21: item #2 (01-Aug-22 - 31-Jan-24); 28: item #2 (01-Aug-22 - 31-Jan-24); 4: item #2 (01-Aug-22 - 31-Jan-24); 11: item #2 (01-Aug-22 - 31-Jan-24); 18: item #2 (01-Aug-22 - 31-Jan-24); 25: item #2 (01-Aug-22 - 31-Jan-24); 2: item #2 (01-Aug-22 - 31-Jan-24); 9: item #2 (01-Aug-22 - 31-Jan-24); 16: item #2 (01-Aug-22 - 31-Jan-24); 23: item #2 (01-Aug-22 - 31-Jan-24); 30: item #2 (01-Aug-22 - 31-Jan-24); 6: item #2 (01-Aug-22 - 31-Jan-24); 13: item #2 (01-Aug-22 - 31-Jan-24); 20: item #2 (01-Aug-22 - 31-Jan-24); 27: item #2 (01-Aug-22 - 31-Jan-24); 4: item #2 (01-Aug-22 - 31-Jan-24); 11: item #2 (01-Aug-22 - 31-Jan-24); 18: item #2 (01-Aug-22 - 31-Jan-24); 25: item #2 (01-Aug-22 - 31-Jan-24); 1: item #2 (01-Aug-22 - 31-Jan-24); 8: item #2 (01-Aug-22 - 31-Jan-24); 15: item #2 (01-Aug-22 - 31-Jan-24); 22: item #2 (01-Aug-22 - 31-Jan-24); 29: item #2 (01-Aug-22 - 31-Jan-24)
| 4 | 1.1 |  | Location |  |  |  | 01-Aug-2022 | 02-Oct-2022 |  | Landscape assessment. | 1: 3 (01-Aug-22 - 02-Oct-22); 8: 3 (01-Aug-22 - 02-Oct-22); 15: 3 (01-Aug-22 - 02-Oct-22); 22: 3 (01-Aug-22 - 02-Oct-22); 29: 3 (01-Aug-22 - 02-Oct-22); 5: 3 (01-Aug-22 - 02-Oct-22); 12: 3 (01-Aug-22 - 02-Oct-22); 19: 3 (01-Aug-22 - 02-Oct-22); 26: 3 (01-Aug-22 - 02-Oct-22)
| 5 | 1.1.1 |  |  | Inspection |  |  | 01-Aug-2022 | 14-Aug-2022 | 2 Weeks | Site visit and inspection of site condition. | 1: 4 (01-Aug-22 - 14-Aug-22); 8: 4 (01-Aug-22 - 14-Aug-22)
| 6 | 1.1.2 |  |  | Preparation |  |  | 15-Aug-2022 | 02-Oct-2022 | 7 Weeks | Preparing the site for further operations. | 15: 5 (15-Aug-22 - 02-Oct-22); 22: 5 (15-Aug-22 - 02-Oct-22); 29: 5 (15-Aug-22 - 02-Oct-22); 5: 5 (15-Aug-22 - 02-Oct-22); 12: 5 (15-Aug-22 - 02-Oct-22); 19: 5 (15-Aug-22 - 02-Oct-22); 26: 5 (15-Aug-22 - 02-Oct-22)
| 7 | 1.1.2.1 |  |  |  | Permission |  | 15-Aug-2022 | 28-Aug-2022 | 2 Weeks | Securing consent from locals and communities nearby. | 15: 6 (15-Aug-22 - 28-Aug-22); 22: 6 (15-Aug-22 - 28-Aug-22)
| 8 | 1.1.2.2 |  |  |  | Clearance of Waste |  | 29-Aug-2022 | 02-Oct-2022 | 5 Weeks | Preparing the site, and route to reach the site for various procurement and other functions. | 29: 7 (29-Aug-22 - 02-Oct-22); 5: 7 (29-Aug-22 - 02-Oct-22); 12: 7 (29-Aug-22 - 02-Oct-22); 19: 7 (29-Aug-22 - 02-Oct-22); 26: 7 (29-Aug-22 - 02-Oct-22)
| 9 | 1.2 |  | Construction |  |  |  | 03-Oct-2022 | 31-Jan-2024 |  | Planning and construction of Phase 1 building structures. | 3: 8 (03-Oct-22 - 31-Jan-24); 10: 8 (03-Oct-22 - 31-Jan-24); 17: 8 (03-Oct-22 - 31-Jan-24); 24: 8 (03-Oct-22 - 31-Jan-24); 31: 8 (03-Oct-22 - 31-Jan-24); 7: 8 (03-Oct-22 - 31-Jan-24); 14: 8 (03-Oct-22 - 31-Jan-24); 21: 8 (03-Oct-22 - 31-Jan-24); 28: 8 (03-Oct-22 - 31-Jan-24); 5: 8 (03-Oct-22 - 31-Jan-24); 12: 8 (03-Oct-22 - 31-Jan-24); 19: 8 (03-Oct-22 - 31-Jan-24); 26: 8 (03-Oct-22 - 31-Jan-24); 2: 8 (03-Oct-22 - 31-Jan-24); 9: 8 (03-Oct-22 - 31-Jan-24); 16: 8 (03-Oct-22 - 31-Jan-24); 23: 8 (03-Oct-22 - 31-Jan-24); 30: 8 (03-Oct-22 - 31-Jan-24); 6: 8 (03-Oct-22 - 31-Jan-24); 13: 8 (03-Oct-22 - 31-Jan-24); 20: 8 (03-Oct-22 - 31-Jan-24); 27: 8 (03-Oct-22 - 31-Jan-24); 6: 8 (03-Oct-22 - 31-Jan-24); 13: 8 (03-Oct-22 - 31-Jan-24); 20: 8 (03-Oct-22 - 31-Jan-24); 27: 8 (03-Oct-22 - 31-Jan-24); 3: 8 (03-Oct-22 - 31-Jan-24); 10: 8 (03-Oct-22 - 31-Jan-24); 17: 8 (03-Oct-22 - 31-Jan-24); 24: 8 (03-Oct-22 - 31-Jan-24); 1: 8 (03-Oct-22 - 31-Jan-24); 8: 8 (03-Oct-22 - 31-Jan-24); 15: 8 (03-Oct-22 - 31-Jan-24); 22: 8 (03-Oct-22 - 31-Jan-24); 29: 8 (03-Oct-22 - 31-Jan-24); 5: 8 (03-Oct-22 - 31-Jan-24); 12: 8 (03-Oct-22 - 31-Jan-24); 19: 8 (03-Oct-22 - 31-Jan-24); 26: 8 (03-Oct-22 - 31-Jan-24); 3: 8 (03-Oct-22 - 31-Jan-24); 10: 8 (03-Oct-22 - 31-Jan-24); 17: 8 (03-Oct-22 - 31-Jan-24); 24: 8 (03-Oct-22 - 31-Jan-24); 31: 8 (03-Oct-22 - 31-Jan-24); 7: 8 (03-Oct-22 - 31-Jan-24); 14: 8 (03-Oct-22 - 31-Jan-24); 21: 8 (03-Oct-22 - 31-Jan-24); 28: 8 (03-Oct-22 - 31-Jan-24); 4: 8 (03-Oct-22 - 31-Jan-24); 11: 8 (03-Oct-22 - 31-Jan-24); 18: 8 (03-Oct-22 - 31-Jan-24); 25: 8 (03-Oct-22 - 31-Jan-24); 2: 8 (03-Oct-22 - 31-Jan-24); 9: 8 (03-Oct-22 - 31-Jan-24); 16: 8 (03-Oct-22 - 31-Jan-24); 23: 8 (03-Oct-22 - 31-Jan-24); 30: 8 (03-Oct-22 - 31-Jan-24); 6: 8 (03-Oct-22 - 31-Jan-24); 13: 8 (03-Oct-22 - 31-Jan-24); 20: 8 (03-Oct-22 - 31-Jan-24); 27: 8 (03-Oct-22 - 31-Jan-24); 4: 8 (03-Oct-22 - 31-Jan-24); 11: 8 (03-Oct-22 - 31-Jan-24); 18: 8 (03-Oct-22 - 31-Jan-24); 25: 8 (03-Oct-22 - 31-Jan-24); 1: 8 (03-Oct-22 - 31-Jan-24); 8: 8 (03-Oct-22 - 31-Jan-24); 15: 8 (03-Oct-22 - 31-Jan-24); 22: 8 (03-Oct-22 - 31-Jan-24); 29: 8 (03-Oct-22 - 31-Jan-24)
| 10 | 1.2.1 |  |  | Design Planning |  |  | 03-Oct-2022 | 23-Oct-2022 | 3 Weeks | Draft preliminary design and schematics. | 3: 9 (03-Oct-22 - 23-Oct-22); 10: 9 (03-Oct-22 - 23-Oct-22); 17: 9 (03-Oct-22 - 23-Oct-22)
| 11 | 1.2.2 |  |  | Discussion and Modification |  |  | 24-Oct-2022 | 06-Nov-2022 | 2 Weeks | Discussion of the ideas with stakeholders and modifying the scheme based on suggestions. | 24: 10 (24-Oct-22 - 06-Nov-22); 31: 10 (24-Oct-22 - 06-Nov-22)
| 12 | 1.2.3 |  |  | Execution |  |  | 07-Nov-2022 | 31-Jan-2024 | 1 Year | Construction of Phase 1 building structures. | 7: 11 (07-Nov-22 - 31-Jan-24); 14: 11 (07-Nov-22 - 31-Jan-24); 21: 11 (07-Nov-22 - 31-Jan-24); 28: 11 (07-Nov-22 - 31-Jan-24); 5: 11 (07-Nov-22 - 31-Jan-24); 12: 11 (07-Nov-22 - 31-Jan-24); 19: 11 (07-Nov-22 - 31-Jan-24); 26: 11 (07-Nov-22 - 31-Jan-24); 2: 11 (07-Nov-22 - 31-Jan-24); 9: 11 (07-Nov-22 - 31-Jan-24); 16: 11 (07-Nov-22 - 31-Jan-24); 23: 11 (07-Nov-22 - 31-Jan-24); 30: 11 (07-Nov-22 - 31-Jan-24); 6: 11 (07-Nov-22 - 31-Jan-24); 13: 11 (07-Nov-22 - 31-Jan-24); 20: 11 (07-Nov-22 - 31-Jan-24); 27: 11 (07-Nov-22 - 31-Jan-24); 6: 11 (07-Nov-22 - 31-Jan-24); 13: 11 (07-Nov-22 - 31-Jan-24); 20: 11 (07-Nov-22 - 31-Jan-24); 27: 11 (07-Nov-22 - 31-Jan-24); 3: 11 (07-Nov-22 - 31-Jan-24); 10: 11 (07-Nov-22 - 31-Jan-24); 17: 11 (07-Nov-22 - 31-Jan-24); 24: 11 (07-Nov-22 - 31-Jan-24); 1: 11 (07-Nov-22 - 31-Jan-24); 8: 11 (07-Nov-22 - 31-Jan-24); 15: 11 (07-Nov-22 - 31-Jan-24); 22: 11 (07-Nov-22 - 31-Jan-24); 29: 11 (07-Nov-22 - 31-Jan-24); 5: 11 (07-Nov-22 - 31-Jan-24); 12: 11 (07-Nov-22 - 31-Jan-24); 19: 11 (07-Nov-22 - 31-Jan-24); 26: 11 (07-Nov-22 - 31-Jan-24); 3: 11 (07-Nov-22 - 31-Jan-24); 10: 11 (07-Nov-22 - 31-Jan-24); 17: 11 (07-Nov-22 - 31-Jan-24); 24: 11 (07-Nov-22 - 31-Jan-24); 31: 11 (07-Nov-22 - 31-Jan-24); 7: 11 (07-Nov-22 - 31-Jan-24); 14: 11 (07-Nov-22 - 31-Jan-24); 21: 11 (07-Nov-22 - 31-Jan-24); 28: 11 (07-Nov-22 - 31-Jan-24); 4: 11 (07-Nov-22 - 31-Jan-24); 11: 11 (07-Nov-22 - 31-Jan-24); 18: 11 (07-Nov-22 - 31-Jan-24); 25: 11 (07-Nov-22 - 31-Jan-24); 2: 11 (07-Nov-22 - 31-Jan-24); 9: 11 (07-Nov-22 - 31-Jan-24); 16: 11 (07-Nov-22 - 31-Jan-24); 23: 11 (07-Nov-22 - 31-Jan-24); 30: 11 (07-Nov-22 - 31-Jan-24); 6: 11 (07-Nov-22 - 31-Jan-24); 13: 11 (07-Nov-22 - 31-Jan-24); 20: 11 (07-Nov-22 - 31-Jan-24); 27: 11 (07-Nov-22 - 31-Jan-24); 4: 11 (07-Nov-22 - 31-Jan-24); 11: 11 (07-Nov-22 - 31-Jan-24); 18: 11 (07-Nov-22 - 31-Jan-24); 25: 11 (07-Nov-22 - 31-Jan-24); 1: 11 (07-Nov-22 - 31-Jan-24); 8: 11 (07-Nov-22 - 31-Jan-24); 15: 11 (07-Nov-22 - 31-Jan-24); 22: 11 (07-Nov-22 - 31-Jan-24); 29: 11 (07-Nov-22 - 31-Jan-24)
| 13 | 1.2.3.1 |  |  |  | Procurement Planning and Sourcing |  | 07-Nov-2022 | 31-Jan-2023 |  | Planning and arranging resources for construction. | 7: 12 (07-Nov-22 - 31-Jan-23); 14: 12 (07-Nov-22 - 31-Jan-23); 21: 12 (07-Nov-22 - 31-Jan-23); 28: 12 (07-Nov-22 - 31-Jan-23); 5: 12 (07-Nov-22 - 31-Jan-23); 12: 12 (07-Nov-22 - 31-Jan-23); 19: 12 (07-Nov-22 - 31-Jan-23); 26: 12 (07-Nov-22 - 31-Jan-23); 2: 12 (07-Nov-22 - 31-Jan-23); 9: 12 (07-Nov-22 - 31-Jan-23); 16: 12 (07-Nov-22 - 31-Jan-23); 23: 12 (07-Nov-22 - 31-Jan-23); 30: 12 (07-Nov-22 - 31-Jan-23)
| 14 | 1.2.3.2 |  |  |  | Building Structures |  | 2023-02-01 | 2024-01-14 |  | Constructing temporary barge ramps, docks, solar panels, outbuildings, camp for working professionals. | 30: 13 (01-Feb-23 - 14-Jan-24); 6: 13 (01-Feb-23 - 14-Jan-24); 13: 13 (01-Feb-23 - 14-Jan-24); 20: 13 (01-Feb-23 - 14-Jan-24); 27: 13 (01-Feb-23 - 14-Jan-24); 6: 13 (01-Feb-23 - 14-Jan-24); 13: 13 (01-Feb-23 - 14-Jan-24); 20: 13 (01-Feb-23 - 14-Jan-24); 27: 13 (01-Feb-23 - 14-Jan-24); 3: 13 (01-Feb-23 - 14-Jan-24); 10: 13 (01-Feb-23 - 14-Jan-24); 17: 13 (01-Feb-23 - 14-Jan-24); 24: 13 (01-Feb-23 - 14-Jan-24); 1: 13 (01-Feb-23 - 14-Jan-24); 8: 13 (01-Feb-23 - 14-Jan-24); 15: 13 (01-Feb-23 - 14-Jan-24); 22: 13 (01-Feb-23 - 14-Jan-24); 29: 13 (01-Feb-23 - 14-Jan-24); 5: 13 (01-Feb-23 - 14-Jan-24); 12: 13 (01-Feb-23 - 14-Jan-24); 19: 13 (01-Feb-23 - 14-Jan-24); 26: 13 (01-Feb-23 - 14-Jan-24); 3: 13 (01-Feb-23 - 14-Jan-24); 10: 13 (01-Feb-23 - 14-Jan-24); 17: 13 (01-Feb-23 - 14-Jan-24); 24: 13 (01-Feb-23 - 14-Jan-24); 31: 13 (01-Feb-23 - 14-Jan-24); 7: 13 (01-Feb-23 - 14-Jan-24); 14: 13 (01-Feb-23 - 14-Jan-24); 21: 13 (01-Feb-23 - 14-Jan-24); 28: 13 (01-Feb-23 - 14-Jan-24); 4: 13 (01-Feb-23 - 14-Jan-24); 11: 13 (01-Feb-23 - 14-Jan-24); 18: 13 (01-Feb-23 - 14-Jan-24); 25: 13 (01-Feb-23 - 14-Jan-24); 2: 13 (01-Feb-23 - 14-Jan-24); 9: 13 (01-Feb-23 - 14-Jan-24); 16: 13 (01-Feb-23 - 14-Jan-24); 23: 13 (01-Feb-23 - 14-Jan-24); 30: 13 (01-Feb-23 - 14-Jan-24); 6: 13 (01-Feb-23 - 14-Jan-24); 13: 13 (01-Feb-23 - 14-Jan-24); 20: 13 (01-Feb-23 - 14-Jan-24); 27: 13 (01-Feb-23 - 14-Jan-24); 4: 13 (01-Feb-23 - 14-Jan-24); 11: 13 (01-Feb-23 - 14-Jan-24); 18: 13 (01-Feb-23 - 14-Jan-24); 25: 13 (01-Feb-23 - 14-Jan-24); 1: 13 (01-Feb-23 - 14-Jan-24); 8: 13 (01-Feb-23 - 14-Jan-24)
| 15 | 1.2.3.2.1 |  |  |  |  | Firepit | 2023-02-01 | 2023-03-03 |  | Construction of Firepit | 30: 1 (01-Feb-23 - 03-Mar-23); 6: 1 (01-Feb-23 - 03-Mar-23); 13: 1 (01-Feb-23 - 03-Mar-23); 20: 1 (01-Feb-23 - 03-Mar-23); 27: 1 (01-Feb-23 - 03-Mar-23)
| 16 | 1.2.3.2.2 |  |  |  |  | Road | 2023-03-06 | 2023-05-26 |  | Construction of Road | 6: 2 (06-Mar-23 - 26-May-23); 13: 2 (06-Mar-23 - 26-May-23); 20: 2 (06-Mar-23 - 26-May-23); 27: 2 (06-Mar-23 - 26-May-23); 3: 2 (06-Mar-23 - 26-May-23); 10: 2 (06-Mar-23 - 26-May-23); 17: 2 (06-Mar-23 - 26-May-23); 24: 2 (06-Mar-23 - 26-May-23); 1: 2 (06-Mar-23 - 26-May-23); 8: 2 (06-Mar-23 - 26-May-23); 15: 2 (06-Mar-23 - 26-May-23); 22: 2 (06-Mar-23 - 26-May-23)
| 17 | 1.2.3.2.3 |  |  |  |  | Camp | 2023-05-29 | 2023-08-04 |  | Construction of Camp | 29: 3 (29-May-23 - 04-Aug-23); 5: 3 (29-May-23 - 04-Aug-23); 12: 3 (29-May-23 - 04-Aug-23); 19: 3 (29-May-23 - 04-Aug-23); 26: 3 (29-May-23 - 04-Aug-23); 3: 3 (29-May-23 - 04-Aug-23); 10: 3 (29-May-23 - 04-Aug-23); 17: 3 (29-May-23 - 04-Aug-23); 24: 3 (29-May-23 - 04-Aug-23); 31: 3 (29-May-23 - 04-Aug-23)
| 18 | 1.2.3.2.4 |  |  |  |  | Barge Ramp | 2023-08-07 | 2023-08-25 |  | Construction of Barge Ramp | 7: 4 (07-Aug-23 - 25-Aug-23); 14: 4 (07-Aug-23 - 25-Aug-23); 21: 4 (07-Aug-23 - 25-Aug-23)
| 19 | 1.2.3.2.5 |  |  |  |  | Wastewater Treatment | 2023-08-28 | 2023-10-27 |  | Construction of Wastewater Treatment | 28: 5 (28-Aug-23 - 27-Oct-23); 4: 5 (28-Aug-23 - 27-Oct-23); 11: 5 (28-Aug-23 - 27-Oct-23); 18: 5 (28-Aug-23 - 27-Oct-23); 25: 5 (28-Aug-23 - 27-Oct-23); 2: 5 (28-Aug-23 - 27-Oct-23); 9: 5 (28-Aug-23 - 27-Oct-23); 16: 5 (28-Aug-23 - 27-Oct-23); 23: 5 (28-Aug-23 - 27-Oct-23)
| 20 | 1.2.3.2.6 |  |  |  |  | Dock | 2023-10-30 | 2024-01-14 |  | Construction of Dock | 30: 6 (30-Oct-23 - 14-Jan-24); 6: 6 (30-Oct-23 - 14-Jan-24); 13: 6 (30-Oct-23 - 14-Jan-24); 20: 6 (30-Oct-23 - 14-Jan-24); 27: 6 (30-Oct-23 - 14-Jan-24); 4: 6 (30-Oct-23 - 14-Jan-24); 11: 6 (30-Oct-23 - 14-Jan-24); 18: 6 (30-Oct-23 - 14-Jan-24); 25: 6 (30-Oct-23 - 14-Jan-24); 1: 6 (30-Oct-23 - 14-Jan-24); 8: 6 (30-Oct-23 - 14-Jan-24)
| 21 | 1.2.3.3 |  |  |  | Reflection |  | 2024-01-15 | 2024-01-31 |  | Getting review from stakeholders for constructions in upcoming phases. | 15: 14 (15-Jan-24 - 31-Jan-24); 22: 14 (15-Jan-24 - 31-Jan-24); 29: 14 (15-Jan-24 - 31-Jan-24)
| 22 | 1.3 |  | Staffing |  |  |  | 2022-11-07 | 2024-01-31 | 1 Year (Simultaneously with Construction) | Planning and staffing various departments with professionals. | 7: 15 (07-Nov-22 - 31-Jan-24); 14: 15 (07-Nov-22 - 31-Jan-24); 21: 15 (07-Nov-22 - 31-Jan-24); 28: 15 (07-Nov-22 - 31-Jan-24); 5: 15 (07-Nov-22 - 31-Jan-24); 12: 15 (07-Nov-22 - 31-Jan-24); 19: 15 (07-Nov-22 - 31-Jan-24); 26: 15 (07-Nov-22 - 31-Jan-24); 2: 15 (07-Nov-22 - 31-Jan-24); 9: 15 (07-Nov-22 - 31-Jan-24); 16: 15 (07-Nov-22 - 31-Jan-24); 23: 15 (07-Nov-22 - 31-Jan-24); 30: 15 (07-Nov-22 - 31-Jan-24); 6: 15 (07-Nov-22 - 31-Jan-24); 13: 15 (07-Nov-22 - 31-Jan-24); 20: 15 (07-Nov-22 - 31-Jan-24); 27: 15 (07-Nov-22 - 31-Jan-24); 6: 15 (07-Nov-22 - 31-Jan-24); 13: 15 (07-Nov-22 - 31-Jan-24); 20: 15 (07-Nov-22 - 31-Jan-24); 27: 15 (07-Nov-22 - 31-Jan-24); 3: 15 (07-Nov-22 - 31-Jan-24); 10: 15 (07-Nov-22 - 31-Jan-24); 17: 15 (07-Nov-22 - 31-Jan-24); 24: 15 (07-Nov-22 - 31-Jan-24); 1: 15 (07-Nov-22 - 31-Jan-24); 8: 15 (07-Nov-22 - 31-Jan-24); 15: 15 (07-Nov-22 - 31-Jan-24); 22: 15 (07-Nov-22 - 31-Jan-24); 29: 15 (07-Nov-22 - 31-Jan-24); 5: 15 (07-Nov-22 - 31-Jan-24); 12: 15 (07-Nov-22 - 31-Jan-24); 19: 15 (07-Nov-22 - 31-Jan-24); 26: 15 (07-Nov-22 - 31-Jan-24); 3: 15 (07-Nov-22 - 31-Jan-24); 10: 15 (07-Nov-22 - 31-Jan-24); 17: 15 (07-Nov-22 - 31-Jan-24); 24: 15 (07-Nov-22 - 31-Jan-24); 31: 15 (07-Nov-22 - 31-Jan-24); 7: 15 (07-Nov-22 - 31-Jan-24); 14: 15 (07-Nov-22 - 31-Jan-24); 21: 15 (07-Nov-22 - 31-Jan-24); 28: 15 (07-Nov-22 - 31-Jan-24); 4: 15 (07-Nov-22 - 31-Jan-24); 11: 15 (07-Nov-22 - 31-Jan-24); 18: 15 (07-Nov-22 - 31-Jan-24); 25: 15 (07-Nov-22 - 31-Jan-24); 2: 15 (07-Nov-22 - 31-Jan-24); 9: 15 (07-Nov-22 - 31-Jan-24); 16: 15 (07-Nov-22 - 31-Jan-24); 23: 15 (07-Nov-22 - 31-Jan-24); 30: 15 (07-Nov-22 - 31-Jan-24); 6: 15 (07-Nov-22 - 31-Jan-24); 13: 15 (07-Nov-22 - 31-Jan-24); 20: 15 (07-Nov-22 - 31-Jan-24); 27: 15 (07-Nov-22 - 31-Jan-24); 4: 15 (07-Nov-22 - 31-Jan-24); 11: 15 (07-Nov-22 - 31-Jan-24); 18: 15 (07-Nov-22 - 31-Jan-24); 25: 15 (07-Nov-22 - 31-Jan-24); 1: 15 (07-Nov-22 - 31-Jan-24); 8: 15 (07-Nov-22 - 31-Jan-24); 15: 15 (07-Nov-22 - 31-Jan-24); 22: 15 (07-Nov-22 - 31-Jan-24); 29: 15 (07-Nov-22 - 31-Jan-24)
| 23 | 1.3.1 |  |  | Hiring |  |  | 07-Nov-2022 | 2023-10-29 |  | Posting jobs and hiring professionals. | 7: 16 (07-Nov-22 - 29-Oct-23); 14: 16 (07-Nov-22 - 29-Oct-23); 21: 16 (07-Nov-22 - 29-Oct-23); 28: 16 (07-Nov-22 - 29-Oct-23); 5: 16 (07-Nov-22 - 29-Oct-23); 12: 16 (07-Nov-22 - 29-Oct-23); 19: 16 (07-Nov-22 - 29-Oct-23); 26: 16 (07-Nov-22 - 29-Oct-23); 2: 16 (07-Nov-22 - 29-Oct-23); 9: 16 (07-Nov-22 - 29-Oct-23); 16: 16 (07-Nov-22 - 29-Oct-23); 23: 16 (07-Nov-22 - 29-Oct-23); 30: 16 (07-Nov-22 - 29-Oct-23); 6: 16 (07-Nov-22 - 29-Oct-23); 13: 16 (07-Nov-22 - 29-Oct-23); 20: 16 (07-Nov-22 - 29-Oct-23); 27: 16 (07-Nov-22 - 29-Oct-23); 6: 16 (07-Nov-22 - 29-Oct-23); 13: 16 (07-Nov-22 - 29-Oct-23); 20: 16 (07-Nov-22 - 29-Oct-23); 27: 16 (07-Nov-22 - 29-Oct-23); 3: 16 (07-Nov-22 - 29-Oct-23); 10: 16 (07-Nov-22 - 29-Oct-23); 17: 16 (07-Nov-22 - 29-Oct-23); 24: 16 (07-Nov-22 - 29-Oct-23); 1: 16 (07-Nov-22 - 29-Oct-23); 8: 16 (07-Nov-22 - 29-Oct-23); 15: 16 (07-Nov-22 - 29-Oct-23); 22: 16 (07-Nov-22 - 29-Oct-23); 29: 16 (07-Nov-22 - 29-Oct-23); 5: 16 (07-Nov-22 - 29-Oct-23); 12: 16 (07-Nov-22 - 29-Oct-23); 19: 16 (07-Nov-22 - 29-Oct-23); 26: 16 (07-Nov-22 - 29-Oct-23); 3: 16 (07-Nov-22 - 29-Oct-23); 10: 16 (07-Nov-22 - 29-Oct-23); 17: 16 (07-Nov-22 - 29-Oct-23); 24: 16 (07-Nov-22 - 29-Oct-23); 31: 16 (07-Nov-22 - 29-Oct-23); 7: 16 (07-Nov-22 - 29-Oct-23); 14: 16 (07-Nov-22 - 29-Oct-23); 21: 16 (07-Nov-22 - 29-Oct-23); 28: 16 (07-Nov-22 - 29-Oct-23); 4: 16 (07-Nov-22 - 29-Oct-23); 11: 16 (07-Nov-22 - 29-Oct-23); 18: 16 (07-Nov-22 - 29-Oct-23); 25: 16 (07-Nov-22 - 29-Oct-23); 2: 16 (07-Nov-22 - 29-Oct-23); 9: 16 (07-Nov-22 - 29-Oct-23); 16: 16 (07-Nov-22 - 29-Oct-23); 23: 16 (07-Nov-22 - 29-Oct-23)
| 24 | 1.3.1.1 |  |  |  | Administrative |  | 14-Aug-2023 | 29-Oct-2023 |  | Hiring staffs for organizational purposes relating to Phase 1 - Clerks, Front Desk, Manager, Communication Specialists. | 14: 17 (14-Aug-23 - 29-Oct-23); 21: 17 (14-Aug-23 - 29-Oct-23); 28: 17 (14-Aug-23 - 29-Oct-23); 4: 17 (14-Aug-23 - 29-Oct-23); 11: 17 (14-Aug-23 - 29-Oct-23); 18: 17 (14-Aug-23 - 29-Oct-23); 25: 17 (14-Aug-23 - 29-Oct-23); 2: 17 (14-Aug-23 - 29-Oct-23); 9: 17 (14-Aug-23 - 29-Oct-23); 16: 17 (14-Aug-23 - 29-Oct-23); 23: 17 (14-Aug-23 - 29-Oct-23)
| 25 | 1.3.1.1.1 |  |  |  |  | Job Posting | 14-Aug-2023 | 01-Oct-2023 |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes | 14: 18 (14-Aug-23 - 01-Oct-23); 21: 18 (14-Aug-23 - 01-Oct-23); 28: 18 (14-Aug-23 - 01-Oct-23); 4: 18 (14-Aug-23 - 01-Oct-23); 11: 18 (14-Aug-23 - 01-Oct-23); 18: 18 (14-Aug-23 - 01-Oct-23); 25: 18 (14-Aug-23 - 01-Oct-23)
| 26 | 1.3.1.1.2 |  |  |  |  | Interview | 04-Sep-2023 | 15-Oct-2023 |  | Reviewing collected applications, filtering, call for interview. | 4: 19 (04-Sep-23 - 15-Oct-23); 11: 19 (04-Sep-23 - 15-Oct-23); 18: 19 (04-Sep-23 - 15-Oct-23); 25: 19 (04-Sep-23 - 15-Oct-23); 2: 19 (04-Sep-23 - 15-Oct-23); 9: 19 (04-Sep-23 - 15-Oct-23)
| 27 | 1.3.1.1.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible | 25-Sep-2023 | 29-Oct-2023 |  | If possible, perform work place test to check adaptability of the prospective staff. | 25: 20 (25-Sep-23 - 29-Oct-23); 2: 20 (25-Sep-23 - 29-Oct-23); 9: 20 (25-Sep-23 - 29-Oct-23); 16: 20 (25-Sep-23 - 29-Oct-23); 23: 20 (25-Sep-23 - 29-Oct-23)
| 28 | 1.3.1.2 |  |  |  | Operations |  | 2023-05-05 | 2023-08-13 |  | Hiring staffs to perform day-to-day operations relating to Phase 1 - Cooks, Canoe Riders, Language Tutors, Healing Therapists/Experts, Recreation Planners, House Keeping | 1: 21 (05-May-23 - 13-Aug-23); 8: 21 (05-May-23 - 13-Aug-23); 15: 21 (05-May-23 - 13-Aug-23); 22: 21 (05-May-23 - 13-Aug-23); 29: 21 (05-May-23 - 13-Aug-23); 5: 21 (05-May-23 - 13-Aug-23); 12: 21 (05-May-23 - 13-Aug-23); 19: 21 (05-May-23 - 13-Aug-23); 26: 21 (05-May-23 - 13-Aug-23); 3: 21 (05-May-23 - 13-Aug-23); 10: 21 (05-May-23 - 13-Aug-23); 17: 21 (05-May-23 - 13-Aug-23); 24: 21 (05-May-23 - 13-Aug-23); 31: 21 (05-May-23 - 13-Aug-23); 7: 21 (05-May-23 - 13-Aug-23)
| 29 | 1.3.1.2.1 |  |  |  |  | Job Posting | 2023-05-05 | 2023-07-23 |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes | 1: 22 (05-May-23 - 23-Jul-23); 8: 22 (05-May-23 - 23-Jul-23); 15: 22 (05-May-23 - 23-Jul-23); 22: 22 (05-May-23 - 23-Jul-23); 29: 22 (05-May-23 - 23-Jul-23); 5: 22 (05-May-23 - 23-Jul-23); 12: 22 (05-May-23 - 23-Jul-23); 19: 22 (05-May-23 - 23-Jul-23); 26: 22 (05-May-23 - 23-Jul-23); 3: 22 (05-May-23 - 23-Jul-23); 10: 22 (05-May-23 - 23-Jul-23); 17: 22 (05-May-23 - 23-Jul-23)
| 30 | 1.3.1.2.2 |  |  |  |  | Interview | 2023-06-05 | 2023-07-30 |  | Reviewing collected applications, filtering, call for interview. | 5: 23 (05-Jun-23 - 30-Jul-23); 12: 23 (05-Jun-23 - 30-Jul-23); 19: 23 (05-Jun-23 - 30-Jul-23); 26: 23 (05-Jun-23 - 30-Jul-23); 3: 23 (05-Jun-23 - 30-Jul-23); 10: 23 (05-Jun-23 - 30-Jul-23); 17: 23 (05-Jun-23 - 30-Jul-23); 24: 23 (05-Jun-23 - 30-Jul-23)
| 31 | 1.3.1.2.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible | 2023-07-03 | 2023-08-13 |  | If possible, perform work place test to check adaptability of the prospective staff. | 3: 24 (03-Jul-23 - 13-Aug-23); 10: 24 (03-Jul-23 - 13-Aug-23); 17: 24 (03-Jul-23 - 13-Aug-23); 24: 24 (03-Jul-23 - 13-Aug-23); 31: 24 (03-Jul-23 - 13-Aug-23); 7: 24 (03-Jul-23 - 13-Aug-23)
| 32 | 1.3.1.3 |  |  |  | Construction |  | 2022-11-07 | 2023-01-22 |  | Hiring staffs for constructions relating to Phase 1. | 7: 25 (07-Nov-22 - 22-Jan-23); 14: 25 (07-Nov-22 - 22-Jan-23); 21: 25 (07-Nov-22 - 22-Jan-23); 28: 25 (07-Nov-22 - 22-Jan-23); 5: 25 (07-Nov-22 - 22-Jan-23); 12: 25 (07-Nov-22 - 22-Jan-23); 19: 25 (07-Nov-22 - 22-Jan-23); 26: 25 (07-Nov-22 - 22-Jan-23); 2: 25 (07-Nov-22 - 22-Jan-23); 9: 25 (07-Nov-22 - 22-Jan-23); 16: 25 (07-Nov-22 - 22-Jan-23)
| 33 | 1.3.1.3.1 |  |  |  |  | Job Posting | 2022-11-07 | 2022-12-11 |  | Coordinate with the construction team for any additions. | 7: 26 (07-Nov-22 - 11-Dec-22); 14: 26 (07-Nov-22 - 11-Dec-22); 21: 26 (07-Nov-22 - 11-Dec-22); 28: 26 (07-Nov-22 - 11-Dec-22); 5: 26 (07-Nov-22 - 11-Dec-22)
| 34 | 1.3.1.3.2 |  |  |  |  | Interview | 2022-11-14 | 2022-12-18 |  |  | 14: 27 (14-Nov-22 - 18-Dec-22); 21: 27 (14-Nov-22 - 18-Dec-22); 28: 27 (14-Nov-22 - 18-Dec-22); 5: 27 (14-Nov-22 - 18-Dec-22); 12: 27 (14-Nov-22 - 18-Dec-22)
| 35 | 1.3.1.3.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible | 2022-12-19 | 2023-01-22 |  |  | 19: 28 (19-Dec-22 - 22-Jan-23); 26: 28 (19-Dec-22 - 22-Jan-23); 2: 28 (19-Dec-22 - 22-Jan-23); 9: 28 (19-Dec-22 - 22-Jan-23); 16: 28 (19-Dec-22 - 22-Jan-23)
| 36 | 1.3.2 |  |  | Training |  |  | 2023-10-16 | 31-Jan-2024 |  | Selection and training staffs on cultural values and community language for better outcomes. | 23: 29 (23-Oct-23 - 31-Jan-24); 30: 29 (23-Oct-23 - 31-Jan-24); 6: 29 (23-Oct-23 - 31-Jan-24); 13: 29 (23-Oct-23 - 31-Jan-24); 20: 29 (23-Oct-23 - 31-Jan-24); 27: 29 (23-Oct-23 - 31-Jan-24); 4: 29 (23-Oct-23 - 31-Jan-24); 11: 29 (23-Oct-23 - 31-Jan-24); 18: 29 (23-Oct-23 - 31-Jan-24); 25: 29 (23-Oct-23 - 31-Jan-24); 1: 29 (23-Oct-23 - 31-Jan-24); 8: 29 (23-Oct-23 - 31-Jan-24); 15: 29 (23-Oct-23 - 31-Jan-24); 22: 29 (23-Oct-23 - 31-Jan-24); 29: 29 (23-Oct-23 - 31-Jan-24)
| 37 | 1.3.2.1 |  |  |  | Planning and Selection |  | 2023-10-16 | 2023-11-12 |  | Analysing and selection of desired staff population for training. | 16: 30 (16-Oct-23 - 12-Nov-23); 23: 30 (16-Oct-23 - 12-Nov-23); 30: 30 (16-Oct-23 - 12-Nov-23); 6: 30 (16-Oct-23 - 12-Nov-23)
| 38 | 1.3.2.2 |  |  |  | Execution |  | 2023-11-27 | 31-Jan-2024 |  | Providing cultural/language training. | 27: 31 (27-Nov-23 - 31-Jan-24); 4: 31 (27-Nov-23 - 31-Jan-24); 11: 31 (27-Nov-23 - 31-Jan-24); 18: 31 (27-Nov-23 - 31-Jan-24); 25: 31 (27-Nov-23 - 31-Jan-24); 1: 31 (27-Nov-23 - 31-Jan-24); 8: 31 (27-Nov-23 - 31-Jan-24); 15: 31 (27-Nov-23 - 31-Jan-24); 22: 31 (27-Nov-23 - 31-Jan-24); 29: 31 (27-Nov-23 - 31-Jan-24)
| 39 | 2 | Phase 2 |  |  |  |  | 2024-02-01 | Jul-25 | 1.5 Years | Construction of external and internal structures; external structures - advancements to basic buildings, more new buildings resonating a healing village, outdoor sctivities area, canoe storage, drinking water well & treatment, and internal structures - meeting area, modifications to interior, healing centre rooms, and front desk & office areas. | bar: 5 to 28
| 40 | 3 | Phase 3 |  |  |  |  | Aug-25 | Jun-26 | 1 Year | Construction of additional zones such as gallery, library & retail spaces and completing the construction for a fully-effectuating cultural healing centre. | bar: 4 to 29