## WBS
Work Breakdown Structure - Building Nawalakw Cultural Healing Centre
Status | ID | SID | Title |  |  |  |  | Duration | Description
| 1 | 0 | Building Nawalakw Cultural Healing Centre |  |  |  |  | 4 Years | Building a healing centre, rejuvenating kwak̓wala language, in three phases.
| 2 | 1 | Phase 1 |  |  |  |  | 1.5 Years | Building small connecting road, temporary barge ramps, fire pit, docks, solar panels, buildings, and camps for consultants & working professionals.
| 3 | 1.1 |  | Location |  |  |  |  | Landscape assessment.
| 4 | 1.1.1 |  |  | Inspection |  |  | 2 Weeks | Site visit and inspection of site condition.
| 5 | 1.1.2 |  |  | Preparation |  |  | 7 Weeks | Preparing the site for further operations.
| 6 | 1.1.2.1 |  |  |  | Permission |  | 2 Weeks | Securing consent from locals and communities nearby.
| 7 | 1.1.2.2 |  |  |  | Clearance of Waste |  | 5 Weeks | Preparing the site, and route to reach the site for various procurement and other functions.
| 8 | 1.2 |  | Construction |  |  |  |  | Planning and construction of Phase 1 building structures.
| 9 | 1.2.1 |  |  | Design Planning |  |  | 3 Weeks | Draft preliminary design and schematics.
| 10 | 1.2.2 |  |  | Discussion and Modification |  |  | 2 Weeks | Discussion of the ideas with stakeholders and modifying the scheme based on suggestions.
| 11 | 1.2.3 |  |  | Execution |  |  | 1 Year | Construction of Phase 1 building structures.
| 12 | 1.2.3.1 |  |  |  | Procurement Planning and Sourcing |  |  | Planning and arranging resources for construction.
| 13 | 1.2.3.2 |  |  |  | Building Structures |  |  | Constructing temporary barge ramps, docks, solar panels, outbuildings, camp for working professionals.
| 14 | 1.2.3.3 |  |  |  | Reflection |  |  | Getting review from stakeholders for constructions in upcoming phases.
| 15 | 1.3 |  | Staffing |  |  |  | 1 Year (Simultaneously with Construction) | Planning and staffing various departments with professionals.
| 16 | 1.3.1 |  |  | Hiring |  |  |  | Posting jobs and hiring professionals.
| 17 | 1.3.1.1 |  |  |  | Administrative |  |  | Hiring staffs for organizational purposes relating to Phase 1 - Clerks, Front Desk, Manager, Communication Specialists.
| 18 | 1.3.1.1.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 19 | 1.3.1.1.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 20 | 1.3.1.1.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 21 | 1.3.1.2 |  |  |  | Operations |  |  | Hiring staffs to perform day-to-day operations relating to Phase 1 - Cooks, Canoe Riders, Language Tutors, Healing Therapists/Experts, Recreation Planners, House Keeping
| 22 | 1.3.1.2.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 23 | 1.3.1.2.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 24 | 1.3.1.2.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 25 | 1.3.1.3 |  |  |  | Construction |  |  | Hiring staffs for constructions relating to Phase 1.
| 26 | 1.3.1.3.1 |  |  |  |  | Job Posting |  | Coordinate with the construction team for any additions.
| 27 | 1.3.1.3.2 |  |  |  |  | Interview
| 28 | 1.3.1.3.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible
| 29 | 1.3.2 |  |  | Training |  |  |  | Selection and training staffs on cultural values and community language for better outcomes.
| 30 | 1.3.2.1 |  |  |  | Planning and Selection |  |  | Analysing and selection of desired staff population for training.
| 31 | 1.3.2.2 |  |  |  | Execution |  |  | Providing cultural/language training.
| 32 | 2 | Phase 2 |  |  |  |  | 1.5 Years | Building external and internal structures; external structures - advancements to basic buildings, more new buildings resonating a healing village, outdoor sctivities area, canoe storage drinking water well & treatment, and internal structures - meeting area, modifications to interior, healing centre rooms, and front desk & office areas.
| 33 | 2.1 |  | Location |  |  |  |  | Landscape assessment for further development.
| 34 | 2.1.1 |  |  | Inspection |  |  | 2 Weeks | Site visit and inspection of site condition.
| 35 | 2.1.2 |  |  | Preparation |  |  |  | Preparing the site for further operations both internally and externally.
| 36 | 2.1.2.1 |  |  |  | Permission |  | 2 Weeks | Securing consent from locals and communities nearby.
| 37 | 2.1.2.2 |  |  |  | Fundraising |  | 4 Weeks | Organising for funds through activities and by calling for sponsors.
| 38 | 2.1.2.3 |  |  |  | Clearance of waste |  | 2 Weeks | Preparing the site for modifications and advanced constructions.
| 39 | 2.2 |  | Construction |  |  |  | 1 Year | Planning and construction of Phase 2 building structures.
| 40 | 2.2.1 |  |  | Design Planning |  |  |  | Draft preliminary design and schematics.
| 41 | 2.2.2 |  |  | Discussion and Modification |  |  |  | Discussion of the ideas with stakeholders and modifying the scheme based on suggestions.
| 42 | 2.2.3 |  |  | Execution |  |  |  | Construction of Phase 2 building structures.
| 43 | 2.2.3.1 |  |  |  | Procurement Planning and Sourcing |  |  | Planning and arranging resources for construction.
| 44 | 2.2.3.2 |  |  |  | Building Structures |  |  | Constructing external structures - advancements to basic buildings, more new buildings resonating a healing village, outdoor sctivities area, canoe storage drinking water well & treatment, and internal structures - meeting area, modifications to interior, healing centre rooms, front desk and office areas.
| 45 | 2.2.3.3 |  |  |  | Reflection |  |  | Getting review from stakeholders on the upgrades.
| 46 | 2.3 |  | Staffing |  |  |  | 1 Year (Simultaneously with Construction) | Adding staffs to various newly constructed departments and healing centre zones.
| 47 | 2.3.1 |  |  | Hiring |  |  |  | Posting jobs and hiring professionals.
| 48 | 2.3.1.1 |  |  |  | Administrative |  |  | Hiring staffs for organizational purposes relating to Phase 2 - Clerks, Front Desk, Manager, Communication Specialists.
| 49 | 2.3.1.1.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 50 | 2.3.1.1.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 51 | 2.3.1.1.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 52 | 2.3.1.2 |  |  |  | Operations |  |  | Hiring staffs to perform day-to-day operations relating to Phase 2 - Cooks, Kayak Riders, Language Tutors, Healing Therapists/Experts, Recreation Planners, House Keeping
| 53 | 2.3.1.2.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 54 | 2.3.1.2.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 55 | 2.3.1.2.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 56 | 2.3.1.3 |  |  |  | Construction |  |  | Hiring staffs for constructions relating to Phase 2.
| 57 | 2.3.1.3.1 |  |  |  |  | Job Posting |  | Coordinate with the construction team for any additions.
| 58 | 2.3.1.3.2 |  |  |  |  | Interview
| 59 | 2.3.1.3.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible
| 60 | 2.3.2 |  |  | Training |  |  |  | Selection and training of any new hires/already existing staffs for better outcomes.
| 61 | 2.3.2.1 |  |  |  | Planning and Selection |  |  | Analysing and selection of desired staff population for training.
| 62 | 2.3.2.2 |  |  |  | Execution |  |  | Providing the required cultural/language training.
| 63 | 3 | Phase 3 |  |  |  |  | 1 Year | Building additional zones such as gallery, library & retail spaces and completing the construction for a fully-effectuating cultural healing centre.
| 64 | 3.1 |  | Location |  |  |  |  | Assessment of the constructed healing centre to check for any possible further developments.
| 65 | 3.1.1 |  |  | Inspection |  |  | 2 Weeks | Site visit and inspection of any possible advancements.
| 66 | 3.1.2 |  |  | Preparation - Fundraising |  |  | 3 Weeks | Organising for funds through activities and by calling for sponsors.
| 67 | 3.2 |  | Construction |  |  |  | 10 Months | Planning and construction of Phase 3 building structures.
| 68 | 3.2.1 |  |  | Design Planning |  |  |  | Draft planned design and schematics.
| 69 | 3.2.2 |  |  | Discussion and Modification |  |  |  | Discussion of the ideas with stakeholders and modifying the scheme based on suggestions.
| 70 | 3.2.3 |  |  | Execution |  |  |  | Construction of Phase 3 building structures.
| 71 | 3.2.3.1 |  |  |  | Procurement Planning and Sourcing |  |  | Planning and arranging resources for construction and add-ons such as books, retail products, certifications and art works.
| 72 | 3.2.3.2 |  |  |  | Building Structures |  |  | Constructing additional zones such as gallery, library & retail spaces
| 73 | 3.2.3.3 |  |  |  | Reflection |  |  | Getting review from stakeholders on the upgrades.
| 74 | 3.3 |  | Staffing |  |  |  | 10 Months | Adding staffs to various newly constructed departments and healing centre zones.
| 75 | 3.3.1 |  |  | Hiring |  |  |  | Posting jobs and hiring professionals.
| 76 | 3.3.1.1 |  |  |  | Administrative |  |  | Hiring staffs for organizational purposes relating to Phase 3 - Cash counter staffs, Front Desk, Manager, Communication Specialists.
| 77 | 3.3.1.1.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 78 | 3.3.1.1.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 79 | 3.3.1.1.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 80 | 3.3.1.2 |  |  |  | Operations |  |  | Hiring staffs to perform day-to-day operations relating to Phase 3 - Language Tutors, Artists, Librarians.
| 81 | 3.3.1.2.1 |  |  |  |  | Job Posting |  | Designing job responsibilities, work related requirements, other requirements, setting duration for applicants to submit their resumes
| 82 | 3.3.1.2.2 |  |  |  |  | Interview |  | Reviewing collected applications, filtering, call for interview.
| 83 | 3.3.1.2.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible |  | If possible, perform work place test to check adaptability of the prospective staff.
| 84 | 3.3.1.3 |  |  |  | Construction |  |  | Hiring staffs for constructions relating to Phase 3 such as interior designers.
| 85 | 3.3.1.3.1 |  |  |  |  | Job Posting |  | Coordinate with the construction team for any additions.
| 86 | 3.3.1.3.2 |  |  |  |  | Interview
| 87 | 3.3.1.3.3 |  |  |  |  | Real time/Workplace Hands-on check – if possible
| 88 | 3.3.2 |  |  | Training |  |  |  | Selection and training of any new hires/already existing staffs for better outcomes.
| 89 | 3.3.2.1 |  |  |  | Planning and Selection |  |  | Analysing and selection of desired staff population for training.
| 90 | 3.3.2.2 |  |  |  | Execution |  |  | Providing the required cultural/language training.